Office Support for City Commissioners

Goal: A funded position for help with marketing, social media, business development, grant management. 1.0 FTE to be hired by June 2018.
Who benefits if this goal is reached? Local city commissioners and other staff in the office.

| Strategies to reach the goal | Resources needed (people, funds, facilities, equipment, incentives, etc.) | Timeline to complete the step | Who will do this? |
| --- | --- | --- | --- |
| Research history of this position – when the last person was hired, what happened to funding | Time | November 2017 | Joe |
| Position description development | Time, ad hoc committee for infrastructure development | December 2017 | Mary and Paul |
| Proposal to City Council to include funding sources, what they will support | Time | January 2018 | Joe |

How will your group stay connected?

- This committee will stay connected through email at checkpoints – October, November, December and January.

- All involved (Joe, Mary, Paul) will take leadership for this.

How will you know when the plan is complete?

- Completion noted when someone is hired.

City Intradepartmental Relationships

Goal: The City Council will host at least six activities during 2018 to increase opportunities for citywide staff (public works, city management, law enforcement, etc.) to interact.

Who benefits if this goal is reached? All city employees and city government

| Strategies to support goals | Resources needed | Timeline | Who is Responsible? |
| --- | --- | --- | --- |
| Citywide picnic – softball or volleyball game | Funds for food, equipment for cooking and games | Fall 2017 | Seth and Brian |